## Sheet1
Phase # | Payment Schedule and Deadline | Module List |  | Users
|  | Name | Functionality | Super Admin | Customer | Salon Admin | Total | Status
Phase1 | 2016-10-29 | Account Management | Add |  | * | * |  | OK
|  |  | View | * | * | *
|  |  | Search | *
|  |  | Update |  | *
|  |  | Delete |  | *
|  | Staff Management | Add |  |  | * |  | OK
|  |  | View | * | * | *
|  |  | Search | * | * | *
|  |  | Update |  |  | *
|  |  | Delete |  |  | *
|  | Services Mngt. | Add |  |  | * |  | OK
|  |  | View | * | * | *
|  |  | Search | * | * | *
|  |  | Update |  |  | *
|  |  | Delete |  |  | *
|  | Promos Mngt. | Add |  |  | * |  | OK
|  |  | View | * | * | *
|  |  | Search | * |  | *
|  |  | Update |  |  | *
|  |  | Delete |  |  | *
|  | Products Mngt. | Add |  |  | * |  | OK
|  |  | View | * | * | *
|  |  | Search | * |  | *
|  |  | Update |  |  | *
|  |  | Delete |  |  | *
|  | Announcement Mngt. | Add |  |  | * |  | OK
|  |  | View | * | * | *
|  |  | Search |  |  | *
|  |  | Update |  |  | *
|  |  | Delete |  |  | *
|  | Calendar Management | Add |  |  | * |  | OK
|  |  | View | * |  | *
|  |  | Search |  |  | *
|  |  | Update |  |  | *
|  |  | Delete |  |  | *
|  | Staff User Management | Add |  |  | * |  | OK
|  |  | View |  |  | *
|  |  | Search |  |  | *
|  |  | Update |  |  | *
|  |  | Delete |  |  | *
TOTAL No of points per module |  |  |  | 12 | 11 | 37 | 60
Phase 2 | To be Determined | Subscription Payment | Add |  | *
|  |  | View | * | * | *
|  |  | Search | *
|  |  | Update |  | * | *
Delete
|  | Reports | Add
|  |  | View |  | *
Search
Update
Delete
|  | Reservation Mngt. | Add |  | *
|  |  | View |  | * | *
|  |  | Search |  | * | *
|  |  | Update |  |  | *
Delete
|  | Customer Reservation Mgt. | Add
View
Search
Update
Delete
|  | Customer Reservation Monitoring | Add
|  |  | View |  | * | *
|  |  | Search |  |  | *
Update
Delete
|  | Services | Add
View
Search
Update
Delete
|  | Staff User Management | Add |  | *
|  |  | View |  | *
|  |  | Search |  | *
|  |  | Update |  | *
|  |  | Delete |  | *
|  |  |  | 2 | 13 | 7 | 22
[6 empty] | TOTAL POINTS | 82
Note on D13: John:
Note on D18: John:
Note on D23: John:
Note on D28: John:
Note on D33: John:
Note on D38: John:
Note on D44: John:
Note on D49: John:
Note on D54: John:
Note on D59: John:
Note on D64: John:
Note on D69: John:
Note on D74: John: